PROJECT PROPOSAL

Voice Room & Social Entertainment Platform

Built with Flutter & Firebase

| Prepared for | Our Esteemed Client |
| --- | --- |
| Document Type | Technical & Commercial Proposal |
| Prepared by | Development Team |
| Date | March 13, 2026 |
| Status | CONFIRMED — We Can Build This |

# Executive Summary

We are pleased to confirm that we can fully design, develop, and deliver the complete Voice Room & Social Entertainment Platform as specified. Our team has thoroughly reviewed all nine functional modules of your requirements and we are confident in our ability to bring this product to life using Flutter for the mobile application and Firebase as the primary backend infrastructure.

This platform — comparable in scope to industry leaders such as BIGO Live and Yalla — is well within our technical capability. Below, we outline how each major feature area will be built, along with our recommended approach, timeline, and team structure.

# Our Capability Confirmation

Here is a direct, module-by-module confirmation of our ability to deliver everything you have requested:

| Feature Module | Technology / Approach | Status |
| --- | --- | --- |
| User Auth & Profiles | Firebase Auth + Firestore + Flutter | ✔ Confirmed |
| Real-Time Voice Rooms | Agora RTC SDK + Firebase Realtime DB | ✔ Confirmed |
| Diamond & Gift System | Firestore Transactions + Lottie Animations | ✔ Confirmed |
| Payment / Recharge | Stripe / Razorpay + Cloud Functions | ✔ Confirmed |
| Mini-Games (Spin/Draw) | Server-side Cloud Functions (provably fair) | ✔ Confirmed |
| VIP & Leaderboards | Firestore + Cloud Functions (scheduled) | ✔ Confirmed |
| Weekly Salary Engine | Firebase Scheduled Functions + Firestore | ✔ Confirmed |
| Social Features & DMs | Firebase Realtime DB + FCM notifications | ✔ Confirmed |
| Admin Panel (Web) | React/Flutter Web + Firebase Admin SDK | ✔ Confirmed |

# Technical Approach

## Mobile Application — Flutter

Flutter is our primary choice for the mobile application, targeting both iOS and Android from a single codebase. Flutter's high-performance rendering engine makes it ideal for the real-time gift animations, entry effects, and interactive UI elements your platform requires. Key packages we will use include Agora Flutter SDK for voice streaming, Lottie and Rive for gift animations, and Provider/Riverpod for state management.

## Backend — Firebase

Firebase covers approximately 80% of all backend needs for this platform natively:

- Firebase Authentication — Phone OTP, Email, Google, and Facebook login

- Cloud Firestore — Real-time data sync for rooms, diamonds, leaderboards, and profiles

- Firebase Realtime Database — Low-latency in-room chat and live event streaming

- Cloud Functions — Server-side game logic, weekly salary distribution, anti-fraud checks

- Firebase Cloud Messaging (FCM) — Push notifications for gifts, followers, salary, and events

- Firebase Storage — Profile photos, gift assets, and room cover images

## Third-Party Services

Two specialized services are required to complement Firebase:

- Agora RTC (or LiveKit) — Real-time voice streaming. Firebase does not provide audio infrastructure. Agora is the industry standard used by BIGO Live and similar platforms.

- Stripe or Razorpay — Secure real-money payment processing for diamond recharge bundles, with full PCI compliance and server-side validation via Cloud Functions.

# Delivery Timeline

We propose a phased delivery approach to ensure quality and allow for client review at each milestone:

| Phase | Duration | Deliverables | Team |
| --- | --- | --- | --- |
| Phase 1 | Months 1–3 | Auth, profiles, basic room creation, voice streaming (Agora), in-room chat | 3 devs |
| Phase 2 | Months 4–6 | Diamond wallet, gift system (15+ gifts), payment integration, XP & levels | 4 devs |
| Phase 3 | Months 7–9 | Mini-games, VIP system, leaderboards, PK battles, admin panel v1 | 4 devs |
| Phase 4 | Months 10–12 | Weekly salary engine, social features, DMs, notifications, polish & QA | 5 devs |
| Phase 5 | Months 13–14 | Performance optimization, security audit, app store submission, launch | Full team |

Total estimated timeline: 12–14 months to full production-ready launch with a team of 4–5 developers working in parallel. A lean MVP (voice rooms, gifts, basic auth) can be delivered in 5–6 months.

# Next Steps

We are ready to move forward immediately. To kick off the project, we propose the following next steps:

- Schedule a detailed discovery call to finalize design references and branding requirements

- Sign the project agreement and confirm the initial milestone

- Begin Phase 1 development within one week of agreement

We are excited about this project and fully committed to delivering a world-class platform. Please do not hesitate to reach out with any questions — we are here to make this vision a reality.

Yes, we can do this. Let's build it.